# ABC’s Inventory Management System

## Key milestones

|  |  |
| --- | --- |
| **Milestone** | **Date** |
| Iteration start | 30/07/2018 |
| Establish Iteration Plan | 30/07/2018 |
| Finalize Transfer Product (Send and Accept Product) features | 31/07/2018 |
| Add ‘Add Staff’ resource in server-side application | 31/07/2018 |
| Add ‘Delete Staff’ resource in server-side application | 01/08/2018 |
| Establish Meeting Minutes and feedback document for week-3 | 02/08/2018 |
| Update Project Plan, Version Control and Risk List | 02/08/2018 |
| Merge all branches on git to keep all branches up to date | 02/08/2018 |
| Add ‘Update Staff’ resource in server-side application | 03/08/2018 |
| Add ‘Add Staff’ and ‘Delete Staff’ feature in client-side application | 04/08/2018 |
| Finalize ‘Manage Product’ features | 05/08/2018 |
| Add ‘Update Staff’ code for server-side and client-side application | 06/08/2018 |
| Add hashing algorithms to store passwords | 07/08/2018 |
| Update Project Plan, Iteration Plan, Risk List and Version Control | 08/08/2018 |
| Finalize Login/ Logout feature for both Store and Warehouse Staff | 09/08/2018 |
| Add server-side and client-side code to check transfer report | 09/08/2018 |
| Finalize Search Product and Manage Product features | 10/08/2018 |
| Establish Meeting Minutes for week-4 | 10/08/2018 |
| Establish Feedback documents for week-4 | 10/08/2018 |
| Update Project Plan, Iteration Plan, Risk List and Version Control | 11/08/2018 |
| Establish Iteration 2 Assessment | 12/08/2018 |
| Iteration Stop | 12/08/2018 |

## High-level objectives

* Finalize Manage Staff, Generate Report, Transfer Stock and Search Product.
* Plan for UI design and development.
* Finalize synchronization of design documentations and implementation.

## Work Item assignments

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Name or key words of description** | **Priority** | **Size estimate (points)** | **State** | **Reference material** | **Target iteration** | **Assigned to (name)** | **Hours worked** | **Estimate of hours remaining** |
| Establish Iteration Plan | 7 | 5 | Completed |  |  | Shirish Maharjan |  |  |
| Finalize Transfer Product (Send and Accept Product) features | 10 | 10 | In Progress |  |  | Hieu Hanh Tran |  |  |
| Add ‘Add Staff’ resource in server-side application | 10 | 10 | In Progress |  |  | Shirish Maharjan |  |  |
| Add ‘Delete Staff’ resource in server-side application | 10 | 10 | In Progress |  |  | Shirish Maharjan |  |  |
| Establish Meeting Minute and Feedback documents for week-3 | 7 | 5 | In Progress |  |  | Arik Maharjan |  |  |
| Update Project Plan, Version Control and Risk List | 10 | 7 | In Progress |  |  | Shirish Maharjan  Hieu Hanh Tran |  |  |
| Merge all branches on git to keep all branches up to date | 10 | 7 | In Progress |  |  | Hieu Hanh Tran  Shirish Maharjan  Arik Maharjan |  |  |
| Add ‘Update Staff’ resource in server-side application | 10 | 9 | In Progress |  |  | Shirish Maharjan |  |  |
| Add ‘Add Staff’ and ‘Delete Staff’ feature in client-side application | 10 | 10 | In Progress |  |  | Shirish Maharjan |  |  |
| Finalize ‘Manage Product’ features | 10 | 10 | In Progress |  |  | Shirish Maharjan |  |  |
| Add ‘Update Staff’ code for server-side and client-side application | 10 | 10 | In Progress |  |  | Shirish Maharjan |  |  |
| Add hashing algorithms to store passwords | 10 | 10 | In Progress |  |  | Shirish Maharjan |  |  |
| Update Project Plan, Iteration Plan, Risk List and Version Control | 7 | 7 | In Progress |  |  | Hieu Hanh Tran  Shirish Maharjan |  |  |
| Finalize Login/ Logout feature for both Store and Warehouse Staff | 10 | 10 | In Progress |  |  | Arik Maharjan |  |  |
| Add server-side and client-side code to check transfer report | 10 | 10 | Not Started |  |  | Hieu Hanh Tran |  |  |
| Finalize Search Product and Manage Product features | 10 | 10 | Not Started |  |  | Hieu Hanh Tran  Shirish Maharjan |  |  |
| Establish Meeting Minutes for week-4 | 7 | 7 | Not Started |  |  | Arik Maharjan |  |  |
| Establish Feedback documents for week-4 | 7 | 7 | Not Started |  |  | Arik Maharjan |  |  |
| Update Project Plan, Iteration Plan, Risk List and Version Control | 7 | 7 | Not Started |  |  | Hieu Hanh Tran  Shirish Maharjan |  |  |
| Establish Iteration 2 Assessment | 9 | 9 | Not Started |  |  | Shirish Maharjan |  |  |

## Issues

|  |  |  |
| --- | --- | --- |
| **Issue** | **Status** | **Notes** |
|  |  |  |

## Evaluation criteria

## Assessment

Will get updated as Iteration is in progress

|  |  |
| --- | --- |
| Assessment target |  |
| Assessment date |  |
| Participants |  |
| Project status |  |

### Assessment against objectives

### Work Items: Planned compared to completed

### Assessment against Evaluation Criteria Test results

### Other concerns and deviations