# ABC’s Inventory Management System

## Iteration 3 Review

## Key milestones

|  |  |
| --- | --- |
| **Milestone** | **Date** |
| Iteration start | 13/08/2018 |
| Establish Iteration Plan | 13/08/2018 |
| Fix Manage Product Bugs | 15/08/2018 |
| Update Domain Model Diagram | 15/08/2018 |
| Establish Meeting Minutes and feedback document for week-5 | 16/08/2018 |
| Update Project Plan, Version Control and Risk List | 16/08/2018 |
| Merge all branches on git to keep all branches up to date | 16/08/2018 |
| Add button hover animation | 17/08/2018 |
| Finalize Manage Product Use Case | 18/08/2018 |
| Add Menu bar for back button, home button and logout option | 19/08/2018 |
| Add wait time animations | 21/08/2018 |
| Finalize ‘Log in and Log out’ use case for both store and warehouse staff | 22/08/2018 |
| Replace buttons with appropriate icons wherever possible. | 22/08/018 |
| Finalize synchronization of FUCD and implementation of all use cases | 22/08/2018 |
| Merge all branches on git | 23/08/2018 |
| Establish Meeting Minutes for week-6 | 23/08/2018 |
| Establish Feedback documents for week-6 | 23/08/2018 |
| Update Project Plan, Iteration Plan, Risk List and Version Control | 23/08/2018 |
| Make application dynamic in terms of resizing and layout | 25/08/2018 |
| Establish Iteration 3 Assessment | 26/08/2018 |
| Iteration Stop | 26/08/2018 |

## High-level objectives

* Finalize synchronization of all FUCD and implementation.
* Finalize Login/Logout and Manage Product.
* Finalize all UI design and implementation.

## Work Item assignments

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Name or key words of description** | **Priority** | **Size estimate (points)** | **State** | **Reference material** | **Target iteration** | **Assigned to (name)** | **Hours worked** | **Estimate of hours remaining** |
| Establish Iteration Plan | 7 | 5 | Completed |  |  | Shirish Maharjan |  |  |
| Fix Manage Product Bugs | 10 | 10 | Completed |  |  | Shirish Maharjan |  |  |
| Update Domain Model Diagram | 10 | 10 | In Progress |  |  | Arik Maharjan |  |  |
| Establish Meeting Minute and Feedback documents for week-5 | 7 | 5 | Completed |  |  | Arik Maharjan |  |  |
| Update Project Plan, Version Control and Risk List | 10 | 7 | Completed |  |  | Shirish Maharjan  Hieu Hanh Tran |  |  |
| Merge all branches on git to keep all branches up to date | 10 | 7 | Completed |  |  | Hieu Hanh Tran  Shirish Maharjan  Arik Maharjan |  |  |
| Add button hover animation | 10 | 9 | In Progress |  |  | Hieu Hanh Tran |  |  |
| Finalize Manage Product Use Case | 10 | 10 | Completed |  |  | Shirish Maharjan |  |  |
| Add Menu bar for back button, home button and logout option | 10 | 10 | In Progress |  |  | Shirish Maharjan |  |  |
| Add wait time animations | 10 | 10 | In Progress |  |  | Shirish Maharjan |  |  |
| Finalize ‘Log in and Log out’ use case for both store and warehouse staff | 10 | 10 | Completed |  |  | Shirish Maharjan  Arik Maharjan |  |  |
| Replace buttons with appropriate icons wherever possible | 10 | 10 | In Progress |  |  | Hieu Hanh Tran |  |  |
| Finalize synchronization of FUCD and implementation of all use cases | 10 | 10 | In Progress |  |  | Arik Maharjan |  |  |
| Merge all branches on git | 9 | 9 | Completed |  |  | Shirish Maharjan  Hieu Hanh Tran  Arik Maharjan |  |  |
| Establish Meeting Minutes for week-6 | 7 | 7 | Not Started |  |  | Arik Maharjan |  |  |
| Establish Feedback documents for week-6 | 7 | 7 | Not Started |  |  | Arik Maharjan |  |  |
| Update Project Plan, Iteration Plan, Risk List and Version Control | 7 | 7 | Not Started |  |  | Hieu Hanh Tran  Shirish Maharjan |  |  |
| Make application dynamic in terms of resizing and layout | 10 | 10 | In Progress |  |  | Shirish Maharjan |  |  |
| Start Work on Test Documents | 10 | 10 | Not Started |  |  | Shirish Maharjan  Hieu Hanh Tran |  |  |
| Establish Iteration 3 Assessment | 9 | 9 | Not Started |  |  | Shirish Maharjan |  |  |

## Issues

|  |  |  |
| --- | --- | --- |
| **Issue** | **Status** | **Notes** |
| Assessment load from other subjects caused delays in completing tasks and adding more tasks to be completed during this iteration. | Discussed | Assessments for other subjects caused more time to be spend outside of the project, however team members are aware of the situation and have discussed about what amount of time needs to be provided for the project regardless of the load from other subjects. |

## Evaluation criteria

## All use cases implemented.

* UI animations and other elements added.
* Test plan updated.

## Assessment

Will get updated as Iteration is in progress

|  |  |
| --- | --- |
| Assessment target |  |
| Assessment date |  |
| Participants |  |
| Project status |  |

### Assessment against objectives

### Work Items: Planned compared to completed

### Assessment against Evaluation Criteria Test results

### Other concerns and deviations