## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | ABC's Inventory Management System |  |  |  |  | Project Name: | ABC's Inventory Management System
National Center: |  |  | Australia |  |  |  |  | National Center: | Australia
Project Manager Name: |  |  | <required> |  |  |  |  | Project Manager Name: | <required>
Project Description: |  |  | ABC's inventory management system help ABC to get detailed and precise information about the stock movement and stock theft. This also allow employees look up current stock contents of the warehouse and each store and then request stock as required. Employees will also be able to send stock digitally i.e. automatically make an update to the database when stock is sent. Moreover, distribution of stock would also be much easier for the warehouse staff as they will know the quantity of each stock for each store. |  |  |  |  | Project Description: | ABC's inventory management system help ABC to get detailed and precise information about the stock movement and stock theft. This also allow employees look up current stock contents of the warehouse and each store and then request stock as required. Employees will also be able to send stock digitally i.e. automatically make an update to the database when stock is sent. Moreover, distribution of stock would also be much easier for the warehouse staff as they will know the quantity of each stock for each store.
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
| Open | Medium | Medium | Yellow | The project might end up being too complicated. The scopes and functionalities of the project cover too much aspects. | The project might not be completed within the timeframe. | Budget Schedule Performance | The use cases or functionalities of the project are more than 12 for a team of 3 members | As soon as the project proposal has been established, if the functionalities are over 15 tasks then implement contigency plan. | Mitigation | Reduce complexity in the functionalities of the system. | Reduce or eliminate the unnecessary functionalities base on the non-functional requiremts.
| Open | High | Medium | Red | The group does not have much expertise in some of the technology that needs to be used in the project. The system requires to work with XML language but the team members only done some simple task by this language before. | The project might not be completed within the timeframe. | Schedule Performance Strategic | The team members did not mention XML skills in their resume | Discuss about the skill set requirements in the team meeting, if none of the team member could use XML then implement contigency plan | Avoidance | Change the XML language to other langue which is more farmiliar with the team members. | Ask helps from other teams or the expertise in XML.
| Open | Low | High | Yellow | Personal issues like work commitment, family, health issues could impact the project or other subject deadlines and exams might affect the schedule of the project. | The project might not be completed within the timeframe. | Schedule Performance | The team members could not attend the team meetings. | The team member confirm that he/she could not complete the tasks. | Monitor and Prepare | Change the XML language to other langue which is more farmiliar with the team members. | Re-schedule the iteration plan to suit with the team members' shcedule
| Open | Medium | Medium | Yellow | Group members might not be enough business data to support the project. | The system might not satisfy the client | Operation Market | The planning documents such as project proposal, iteration plan, etc. are confusing and cannot point out the goal of the project. |  | Monitor and Prepare | Conduct the researchs and surveys about the company to get more informaiton about current bussiness
| Open | Medium | Low | Green | The client does not like the final products. | The project might be restart again or have to be put in the canceled | Operation Market | Client gave the negative feedbacks through the reports and documents. |  | Monitor and Prepare | Conduct the meeting between the team and client to get more requirements and feedbacks then re-design or add more functionalities which are required.
| Closed | High | Medium | Closed | The team members might be working without any synergy between them, always fighting with each other, blaming and passing the buck, without actual focus on the problem. | The project could be delayed or canceled. | Performance Operational | There are the negative non-verbal actions or fighting in the team meetings. | The team members changed/ fixed others'tasks | Monitor and Prepare | Making sure that everyone is at a good understanding of the assignment when doing them. Everyone will be expected to stay professional and not prejudge immaturely. | The manager will have the right to give the punishment to the one did not follow the team rules.
Note on A6: • ID: A unique ID number used to identify the risk in the risk management log.
Note on B6: • Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
Note on C6: • Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
Note on D6: • Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue. o High: Greater than 70% probability of occurrence. o Medium: Between 30% and 70% probability of occurrence. o Low: Below 30% probability of occurrence.
Note on E6: • Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
Note on F6: • Risk Description: This column should be populated with a description of the risk.
Note on G6: • Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
Note on H6: • Risk Area: This column should be populated with the appropriate risk area.
Note on I6: • Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
Note on J6: • Triggers: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
Note on K6: Risk Response Strategy: This column should be populated with the preferred risk response strategy.
Note on L6: • ResponseStrategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
Note on M6: • Contingency Plan: This column should be populated with a description of the risk contingency plan.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources